## Dışa Aktarma Özeti
Bu belge Numbers’dan dışa aktarıldı. Her bir tablo Excel çalışma sayfasına dönüştürüldü. Her bir Numbers sayfasındaki diğer tüm nesneler ayrı çalışma sayfalarına yerleştirildi. Lütfen formül hesaplamalarının Excel’de farklı olabileceğini unutmayın.
Numbers Sayfası Adı | Numbers Tablosu Adı | Excel Çalışma Sayfası Adı
02 TECHNOLOGY STACK
| Tablo 1 | 02 TECHNOLOGY STACK
05 ADMIN PANEL PAGES
| Tablo 1 | 05 ADMIN PANEL PAGES
01 INFRASTRUCTURE
| Tablo 1 | 01 INFRASTRUCTURE
04 MOBILE APP SCREENS
| Tablo 1 | 04 MOBILE APP SCREENS
03 WEBSITE PAGES
| Tablo 1 | 03 WEBSITE PAGES
06 TESTING and QA
| Tablo 1 | 06 TESTING and QA
07 DEPLOYMENT
| Tablo 1 | 07 DEPLOYMENT
SECURITY CHECKLIST
| Tablo 1 | SECURITY CHECKLIST
PERFORMANCE METRICS
| Tablo 1 | PERFORMANCE METRICS
COMPLIANCE
| Tablo 1 | COMPLIANCE
LAUNCH CHECKLIST
| Tablo 1 | LAUNCH CHECKLIST
DELIVERY CHECKLIST
| Tablo 1 | DELIVERY CHECKLIST
POST LAUNCH
| Tablo 1 | POST LAUNCH

## 02 TECHNOLOGY STACK
Category | Technology | Purpose
Frontend Web | React/Next.js or Vue/Nuxt.js | Server-side rendering, SEO optimization
Frontend Web | TypeScript | Type safety and better code quality
Frontend Web | Tailwind CSS / Material UI | Responsive styling framework
Mobile App | React Native or Flutter | Cross-platform mobile development
Backend | Node.js with Express/Nest.js | API server and business logic
Backend | Python with Django/FastAPI | Alternative for ML features
Database | PostgreSQL 15 | Primary relational database
Database | Redis 7.0 | Caching and session storage
Database | Elasticsearch/Algolia | Advanced search functionality
Hosting | Servers | Scalable cloud infrastructure
File Storage | File Storage | Image and file storage | minio
CDN | CloudFlare / CloudFront | Content delivery network
Authentication | JWT + OAuth 2.0 | Secure authentication
Payment | Izyico | Payment processing
Email | SendGrid / Amazon SES | Transactional emails
Push Notifications | Firebase Cloud Messaging | Mobile push notifications
Analytics | Google Analytics 4 | Web and app analytics
Analytics | Firebase Analytics | Mobile app analytics
Monitoring | New Relic / Datadog | Application performance monitoring | graphana ve promethius var
Error Tracking | Sentry | Error and crash tracking
Logging | ELK Stack | Centralized logging | loki + promtail
CI/CD | GitHub Actions / GitLab CI | Automated deployment pipeline
Version Control | Git (GitHub/GitLab) | Source code management
Testing | Jest / Cypress | Unit and E2E testing | jest + playwright
Load Testing | JMeter / Artillery | Performance testing
Documentation | Swagger/OpenAPI | API documentation | swagger
Localization | react-i18next / vue-i18n | Multi-language support
Real-time | Socket.io / WebSockets | Real-time chat and notifications
Message Queue | RabbitMQ / AWS SQS | Asynchronous processing
Containerization | Docker | Application containerization
Orchestration | Kubernetes (optional) | Container orchestration

## 05 ADMIN PANEL PAGES
ID | Page Name | Key Features
A1 | Admin Login Page | Secure login, 2FA, IP whitelist, session timeout
A2 | Dashboard/Overview | KPIs, sales charts, recent orders, user stats, quick actions
A3 | Analytics Page | Revenue reports, traffic stats, conversion rates, custom date ranges
A4 | Sales Reports | Daily/monthly/yearly sales, export CSV/PDF, charts, comparisons
A5 | Orders List | All orders, filter by status, search, bulk actions, export
A6 | Order Detail Page | Order info, customer details, items, payment status, actions (refund, cancel)
A7 | Order Status Management | Update status, add tracking, send notifications, print invoice/label | takip ekleme bildirim ve fatura yazdırma yok
A8 | Refunds & Returns | Return requests, process refunds, approval workflow, history | iade geçmişi sayfası yok
A9 | Products List | All products, search, filter, bulk edit, import/export | import export yok
A10 | Add Product Page | Product form, images, specs, pricing, inventory, SEO fields | admin ürün eklemesi yok
A11 | Edit Product Page | Modify product details, update images, pricing, stock | tam ürün düzenleme formu yok
A12 | Bulk Product Upload | CSV import, field mapping, validation, preview, import
A13 | Inventory Management | Stock levels, low stock alerts, reorder points, stock history
A14 | Product Reviews Management | Moderate reviews, approve/reject, respond, filter spam | ürün yorumları sayfası yok ekstra olarak
A15 | Categories Management | Add/edit/delete categories, hierarchy, drag-drop reorder, images | drag drop sıralama tam değil
A16 | Manufacturers Management | Add/edit manufacturers, logos, descriptions, product count
A17 | Collections Management | Create collections, add products, set visibility, featured
A18 | Tags Management | Manage product tags, merge tags, bulk assign
A19 | Attributes Management | Define attributes (scale, condition, color), values, groups
A20 | Users List | All users, search, filter by role, status, registration date
A21 | User Detail Page | User info, order history, activity log, ban/suspend, edit
A22 | Sellers Management | Seller applications, approval, commission settings, performance | ayrı olarak satıcı başvuru onay ve satıcı performans sayfası yok
A23 | Roles & Permissions | Define roles, assign permissions, user role assignment | admin panelde rol yönetim sayfası yok
A24 | Membership Management | View members, manage subscriptions, benefits, cancellations
A25 | Pages Management | Static pages (About, FAQ), WYSIWYG editor, SEO settings
A27 | FAQ Management | Add/edit FAQs, categories, reorder, search
A28 | Banner/Slider Management | Homepage banners, images, links, scheduling, position
A29 | Email Templates | Edit email templates, variables, preview, send test
A30 | Coupons/Discounts | Create coupons, discount codes, percentage/fixed, validity, usage limits
A31 | Promotions Management | Flash sales, bulk discounts, BOGO, scheduling
A32 | Trade Requests | Pending trades, monitor trades, dispute resolution, approve/reject
A33 | Trade Analytics | Trade volume, popular items, success rates, user engagement | ayrı analitik sayfası , detaylı metrikler sınırlı
A34 | Payments & Transactions | All transactions, payment status, refunds, filter by gateway
A35 | Seller Payouts | Calculate payouts, payment schedule, transaction history, export | satıcı banka bilgisi yok ve payout api gerekli
A36 | Commission Settings | Set commission rates, per category/seller, history
A37 | Tax Settings | Tax rates by region, tax rules, reporting
A38 | Shipping Methods | Add/edit shipping methods, rates, zones, carriers
A39 | Shipping Labels | Generate labels, bulk printing, carrier integration
A40 | Shipping Zones | Define zones, set rates, country/region mapping
A41 | Messages Management | Monitor user messages, spam detection, moderation
A42 | Support Tickets | Customer support tickets, assign, respond, track, close
A43 | Notifications Management | Send push/email notifications, templates, scheduling, history
A44 | General Settings | Site name, logo, contact info, timezone, currency, language | logo timezone currency tam değil
A45 | Payment Settings | Payment gateways, API keys, test/live mode, currencies | ayrı ödeme ayarları sayfası yok
A46 | Email Settings | SMTP config, sender details, test email
A47 | Social Media Settings | OAuth credentials, API keys, social links
A48 | Security Settings | SSL, firewall rules, IP blocking, session timeout, 2FA | ayrı güvenlik sayfası yok
A49 | API Settings | API keys, webhooks, rate limits, documentation
A50 | Cache Management | Clear cache, cache settings, performance optimization
A51 | Activity Logs | System logs, user actions, admin actions, export logs
A52 | Error Logs | Application errors, stack traces, filter by severity
A53 | Security Logs | Failed logins, suspicious activity, IP blocks
A54 | Email Logs | Sent emails, delivery status, bounces, opens/clicks
A55 | Customer Reports | Customer acquisition, lifetime value, retention, segmentation | ayrı müşteri retention/segment raporu yok
A56 | Backup & Restore | Database backup, scheduled backups, restore, download
A57 | System Updates | Update notifications, change logs, update installation
A58 | Database Management | Database optimization, repair, query logs
A59 | File Manager | Upload/manage files, images, organize folders, bulk actions | reklar için medya yükleme var ama tam dosya yöneticisi yok
A60 | Translation Management | Language files, edit translations, import/export

## 01 INFRASTRUCTURE
Category | Requirement | Status | Owner | Notes
Infrastructure | Production Server hosting | Pending |  | Choose provider based on budget
Infrastructure | Pre-Production Server hosting | Pending |  | Choose provider based on budget
Infrastructure | Development and UAT Server hosting | Pending |  | Choose provider based on budget
Infrastructure | Web Application Servers configuration detals | Pending |  | Auto-scaling configured
Infrastructure | Database Servers configuration details | Pending |  | Choose DB
Infrastructure | Redis Cache Server configuration details | Pending |  | For session and query caching
Infrastructure | CDN Setup (CloudFlare/CloudFront) | Pending |  | Cache static assets 1 year
Infrastructure | Load Balancer Configuration | Pending |  | Health checks every 30s | Traefik var, health checks var
Infrastructure | Auto-scaling rules (CPU > 70%) | Pending |  | Horizontal scaling | docker-compose.prod.yml'de CPU-based scaling config var
Database | PostgreSQL/MySQL installation and configuration | Pending |  | Max connections 200-500
Database | Database optimization (indexes, query performance) | Pending |  | Target < 50ms average
Database | Master-slave replication setup | Pending |  | High availability
Database | Automated backup system (daily full, hourly incremental) | Pending |  | 30-day retention
Database | Point-in-time recovery capability | Pending |  | Critical for data recovery
Database | Database encryption at rest | Pending |  | For sensitive data
Database | Automated failover mechanism | Pending |  | Minimize downtime
Security | SSL/TLS Certificate | Pending |  | Auto-renewal configured | lets encrypt
Security | TLS 1.2/1.3 configuration with strong ciphers | Pending |  | Target SSL Labs A+
Security | HSTS header implementation | Pending |  | Max-age 31536000
Security | Security headers (CSP, X-Frame-Options, etc.) | Pending |  | Prevent XSS, clickjacking
Security | Input validation and sanitization | Pending |  | All user inputs
Security | SQL injection prevention (parameterized queries) | Pending |  | Critical security
Security | XSS prevention (DOMPurify) | Pending |  | Sanitize HTML
Security | Password hashing (bcrypt/Argon2, 12+ rounds) | Pending |  | Strong security
Security | Strong password policy enforcement | Pending |  | 8+ chars, mixed case, symbols
Security | Account lockout after failed login attempts | Pending |  | 5 attempts, 15 min lockout
Security | JWT implementation (15min access, 7 day refresh) | Pending |  | Secure cookies
Security | CSRF protection tokens | Pending |  | All state-changing requests
Security | Rate limiting implementation | Pending |  | Prevent abuse
Security | DDoS protection at CDN level | Pending |  | CloudFlare/AWS Shield
Security | File upload validation (type, size, content) | Pending |  | Prevent malicious uploads
Security | Security audit and penetration testing | Pending |  | Before launch
Security | WAF (Web Application Firewall) setup | Pending |  | Choose WAF
Security | 2FA/MFA implementation | Pending |  | Optional for users
Payment | Payment gateway integration (Izyico) | Pending |  | PCI DSS compliant | sandbox kurulu api gelince düzelecek
Payment | Tokenization for card storage | Pending |  | Never store CVV
Payment | 3D Secure authentication | Pending |  | Fraud prevention
Payment | Payment transaction audit logs | Pending |  | Compliance requirement
Payment | Fraud detection system (velocity checks) | Pending |  | Geolocation, patterns
Payment | Quarterly vulnerability scans | Pending |  | PCI DSS requirement
Payment | Refund and chargeback handling | Pending |  | Automated workflows
SEO | Server-side rendering (Next.js/Nuxt.js) | Pending |  | Better SEO | ssr optimizasyonu eksik
SEO | Clean URL structure implementation | Pending |  | Hyphens, descriptive | kısmen var tam değil
SEO | XML sitemap generation (auto-update) | Pending |  | Submit to search engines | sitemap var auto update yok
SEO | Robots.txt configuration | Pending |  | Block admin, duplicates
SEO | Meta tags optimization (title, description) | Pending |  | Unique per page
SEO | Open Graph and Twitter Card tags | Pending |  | Social sharing
SEO | Structured data (Schema.org JSON-LD) | Pending |  | Product, Review, Organization
SEO | Image optimization and lazy loading | Pending |  | WebP with fallbacks
SEO | Core Web Vitals optimization | Pending |  | LCP<2.5s, FID<100ms, CLS<0.1
SEO | Mobile-first responsive design | Pending |  | Google mobile-first indexing | google mobile first indexing optimizasyonu eksik
SEO | AI Search Optimization (SearchGPT, Perplexity) | Pending |  | Structured answers, FAQs
SEO | Internal linking strategy | Pending |  | Keyword-rich anchors
SEO | Canonical tags for duplicate content | Pending |  | Prevent duplicate indexing
SEO | Google Search Console setup | Pending |  | Monitor performance
Email | Transactional email service | Pending |  | API integration
Email | SPF record configuration | Pending |  | Email authentication
Email | DKIM setup | Pending |  | Email authentication
Email | DMARC policy configuration | Pending |  | Email security
Email | Email template system (MJML) | Pending |  | Responsive templates
Email | Welcome email automation | Pending |  | After registration
Email | Email verification flow | Pending |  | Confirm email ownership
Email | Password reset email | Pending |  | Secure token-based
Email | Order confirmation emails | Pending |  | With invoice PDF | invoice pdf yok
Email | Shipping notification emails | Pending |  | Tracking info | tracking sayfasına yönlendiriyo ama güncellemelerin mail gelmesi için api lazım
Email | Trade proposal notification | Pending |  | Real-time alerts
Email | Message notification emails | Pending |  | User inbox alerts
Email | Email unsubscribe functionality | Pending |  | Legal requirement
Email | Email bounce handling | Pending |  | Track bounced emails
Localization | i18n framework setup (react-i18next/vue-i18n) | Pending |  | Multi-language support
Localization | Language detection (browser, user preference) | Pending |  | Auto-detect language
Localization | Translation files structure (JSON/YAML) | Pending |  | Organized by page/feature
Localization | RTL (Right-to-Left) support for Arabic | Pending |  | CSS RTL support
Localization | Currency localization | Pending |  | Multi-currency support
Localization | Date/time localization | Pending |  | Format per locale
Localization | Number formatting localization | Pending |  | Decimal separators
Localization | Language selector UI component | Pending |  | Easy switching
Localization |  | Pending |  | Proper indexing
Localization | Translation management system | Pending |  | Lokalise/Crowdin
Localization | Initial languages: English, Turkish | Pending |  | Expand later
Push Notifications | Firebase Cloud Messaging (FCM) setup | Pending |  | For Android
Push Notifications | Apple Push Notification Service (APNs) setup | Pending |  | For iOS
Push Notifications | Push notification permission handling | Pending |  | User opt-in
Push Notifications | Device token management | Pending |  | Store and update tokens
Push Notifications | Notification categories (orders, messages, trades) | Pending |  | User preferences
Push Notifications | Rich notifications (images, actions) | Pending |  | Enhanced engagement
Push Notifications | Deep linking from notifications | Pending |  | Direct to content
Push Notifications | Notification scheduling system | Pending |  | Time-based sending | notificationlar çalışıyor ama burada istenenler kadarı yok
Push Notifications | Notification analytics tracking | Pending |  | Open rates, clicks
Push Notifications | Notification preference center | Pending |  | User controls
Push Notifications | Badge count management | Pending |  | Unread indicators
Push Notifications | Silent/background notifications | Pending |  | Data sync
Social Media | Facebook Login integration | Pending |  | OAuth 2.0
Social Media | Google Login integration | Pending |  | OAuth 2.0
Social Media | Apple Sign In (iOS) | Pending |  | Required for App Store
Social Media | Social sharing buttons (Facebook, Twitter, WhatsApp) | Pending |  | Product pages
Social Media | Instagram integration for product photos | Pending |  | User gallery
Social Media | Social media API rate limit handling | Pending |  | Prevent blocks
Social Media | Social login account linking | Pending |  | Merge accounts
Analytics | Google Analytics 4 (GA4) implementation | Pending |  | Full event tracking
Analytics | Google Tag Manager setup | Pending |  | Manage tags easily
Analytics | E-commerce tracking (transactions, revenue) | Pending |  | Purchase funnel
Analytics | User behavior tracking (page views, clicks) | Pending |  | Understand users
Analytics | Conversion funnel tracking | Pending |  | Optimize conversions
Analytics | Custom event tracking | Pending |  | Product views, searches
Analytics | User session recording (Hotjar/FullStory) | Pending |  | Heatmaps, recordings
Analytics | Error tracking (Sentry/Rollbar) | Pending |  | Monitor bugs
Analytics | Performance monitoring (New Relic/Datadog) | Pending |  | APM
Analytics | Custom analytics dashboard | Pending |  | Admin insights
Analytics | Facebook Pixel implementation | Pending |  | Retargeting
Analytics | LinkedIn Insight Tag | Pending |  | B2B tracking
Firebase | Firebase project setup | Pending |  | For mobile app
Firebase | Firebase Authentication | Pending |  | User auth for app
Firebase | Firebase Cloud Firestore (if needed) | Pending |  | NoSQL database
Firebase | Firebase Storage for images | Pending |  | User uploads
Firebase | Firebase Analytics | Pending |  | App usage tracking
Firebase | Firebase Crashlytics | Pending |  | Crash reporting
Firebase | Firebase Remote Config | Pending |  | Feature flags
Firebase | Firebase Dynamic Links | Pending |  | Deep linking
Firebase | Firebase Performance Monitoring | Pending |  | App performance
Firebase | Firebase App Distribution | Pending |  | Beta testing
Development | Git repository setup (GitHub/GitLab/Bitbucket) | Pending |  | Version control
Development | Branch strategy (Git Flow/Trunk-based) | Pending |  | Feature branches
Development | Code review process | Pending |  | Pull request reviews
Development | Commit message conventions | Pending |  | Conventional commits
Development | Repository access control | Pending |  | Role-based access
Development | .gitignore configuration | Pending |  | Exclude sensitive files
Development | Repository backup strategy | Pending |  | Redundancy
CI/CD | CI/CD platform setup (GitHub Actions/GitLab CI/Jenkins) | Pending |  | Automated pipeline
CI/CD | Automated testing on commit | Pending |  | Unit, integration tests
CI/CD | Code quality checks (ESLint, SonarQube) | Pending |  | Maintain quality
CI/CD | Security scanning (dependency vulnerabilities) | Pending |  | Snyk/Dependabot
CI/CD | Automated deployment to staging | Pending |  | After tests pass
CI/CD | Manual approval for production | Pending |  | Release control
CI/CD | Blue-green deployment strategy | Pending |  | Zero downtime
CI/CD | Rollback capability | Pending |  | Quick recovery
CI/CD | Environment variable management | Pending |  | Secure config
CI/CD | Build artifact storage | Pending |  | Version history
CI/CD | Deployment notifications (Slack/Email) | Pending |  | Team awareness
Privacy | Cookie consent banner | Pending |  | GDPR compliance
Privacy | Cookie policy page | Pending |  | Detailed cookie info | Var ancak gelistirilmeli
Privacy | Privacy policy page | Pending |  | Lawyer-reviewed | Lawyer reviewed degiller
Privacy | Terms of service page | Pending |  | Lawyer-reviewed
Privacy | Data export functionality (GDPR) | Pending |  | JSON/CSV export
Privacy | Account deletion with data anonymization | Pending |  | Right to erasure
Privacy | Consent management system | Pending |  | Track consent
Privacy | Data Protection Officer contact info | Pending |  | GDPR requirement
Privacy | User preference center | Pending |  | Manage privacy settings
Privacy | Data retention policy implementation | Pending |  | Auto-delete old data
Performance | Code minification (JS, CSS) | Pending |  | Reduce file size
Performance | Code splitting and lazy loading | Pending |  | Load on demand
Performance | Image optimization pipeline | Pending |  | WebP conversion
Performance | Gzip/Brotli compression | Pending |  | Compress responses
Performance | Redis caching implementation | Pending |  | Frequent queries
Performance | HTTP caching headers | Pending |  | ETag, Last-Modified
Performance | Database query optimization | Pending |  | Indexes, EXPLAIN
Performance | Database connection pooling | Pending |  | Efficient connections
Performance | API response caching | Pending |  | 5-15 min TTL
Performance | Service worker for offline support | Pending |  | PWA capability
Testing | Unit testing setup (Jest/Mocha) | Pending |  | 80%+ coverage
Testing | Integration testing | Pending |  | API endpoints
Testing | E2E testing (Cypress/Playwright) | Pending |  | Critical flows
Testing | Cross-browser testing | Pending |  | Chrome, Firefox, Safari, Edge
Testing | Mobile device testing | Pending |  | Various screen sizes
Testing | Load testing (JMeter/Artillery) | Pending |  | 500-1000 concurrent users
Testing | API testing (Postman/Newman) | Pending |  | All endpoints
Testing | Accessibility testing (WCAG 2.1) | Pending |  | A11y compliance
Testing | Security testing (OWASP Top 10) | Pending |  | Vulnerability scan
Testing | User acceptance testing (UAT) | Pending |  | Client sign-off
Monitoring | Application monitoring (New Relic/Datadog/Prometheus) | Pending |  | Performance metrics
Monitoring | Centralized logging (ELK Stack) | Pending |  | Log aggregation
Monitoring | Error tracking (Sentry/Rollbar) | Pending |  | Bug tracking
Monitoring | Uptime monitoring (Pingdom/UptimeRobot) | Pending |  | 24/7 availability
Monitoring | Alert rules configuration | Pending |  | Critical issues
Monitoring | Performance dashboards | Pending |  | Real-time metrics
Monitoring | Database performance monitoring | Pending |  | Query analysis
Monitoring | API response time monitoring | Pending |  | Target <200ms
Monitoring | SSL certificate expiration monitoring | Pending |  | Auto-alerts
Monitoring | On-call rotation setup | Pending |  | Incident response
Documentation | API documentation (Swagger/OpenAPI) | Pending |  | Auto-generated
Documentation | System architecture documentation | Pending |  | Diagrams, explanations
Documentation | Database schema documentation | Pending |  | ERD diagrams
Documentation | Deployment runbook | Pending |  | Step-by-step guide
Documentation | Incident response playbook | Pending |  | Emergency procedures
Documentation | User manual/help documentation | Pending |  | End-user guide
Documentation | Admin panel documentation | Pending |  | Admin features
Documentation | Code comments and inline documentation | Pending |  | Complex functions
Mobile App | React Native/Flutter framework setup | Pending |  | Cross-platform
Mobile App | iOS app development | Pending |  | Swift/React Native
Mobile App | Android app development | Pending |  | Kotlin/React Native
Mobile App | App icon and splash screen | Pending |  | All screen sizes
Mobile App | App Store listing preparation | Pending |  | Screenshots, description
Mobile App | Google Play listing preparation | Pending |  | Screenshots, description
Mobile App | In-app purchases setup (if applicable) | Pending |  | Subscriptions
Mobile App | Biometric authentication (Face ID/Fingerprint) | Pending |  | Enhanced security
Mobile App | Offline mode capability | Pending |  | Cache data locally
Mobile App | App update mechanism | Pending |  | Force/optional updates
Mobile App | App version management | Pending |  | Track versions
Mobile App | Device compatibility testing | Pending |  | Various devices
Features | Search functionality (Elasticsearch/Algolia) | Pending |  | Fast product search
Features | Advanced filters and sorting | Pending |  | Multi-faceted search
Features | Help desk/ticketing system | Pending |  | Customer support | iyilestirilebilir
Features | Admin dashboard analytics | Pending |  | Business insights
Features | Inventory management | Pending |  | Stock tracking
Features | Shipping integration | Pending |  | Automated shipping
Features | Invoice generation (PDF) | Pending |  | Purchase records

## 04 MOBILE APP SCREENS
ID | Screen Name | Key Features
M1 | Splash Screen | App logo, loading animation, version check
M2 | Onboarding Screens | Feature introduction, swipe carousel, skip option
M3 | Login Screen | Email/password, social login, biometric login, forgot password
M4 | Registration Screen | Sign up form, social signup, terms acceptance
M5 | Forgot Password Screen | Email input, send reset link, back to login
M6 | Home Screen | Featured products, categories, search, notifications badge, bottom nav
M7 | Search Screen | Search bar, filters, recent searches, suggestions, voice search
M8 | Categories Screen | All categories grid, icons, product counts
M9 | Account/Profile Screen | User info, menu options, settings, logout
M10 | Product Listing Screen | Product grid/list, filters drawer, sort options, pull to refresh
M11 | Product Detail Screen | Image carousel, zoom, specs, price, add to cart, share, reviews
M12 | Shopping Cart Screen | Cart items, swipe to delete, quantity controls, checkout button
M13 | Checkout Screen | Address selection, delivery options, payment method, order summary
M14 | Payment Screen | Payment form, saved cards, security badges, pay button
M15 | Order Success Screen | Order confirmation, order number, track order, home button
M16 | My Orders Screen | Order list, filter by status, search orders, order cards
M17 | Order Detail Screen | Order items, status timeline, tracking, invoice download, contact seller
M18 | Order Tracking Screen | Map view, delivery status, carrier info, contact driver
M19 | Wishlist Screen | Saved products, remove items, add to cart, share
M20 | Profile Edit Screen | Edit personal info, profile photo, save changes
M21 | Address Book Screen | Saved addresses, add/edit/delete, set default
M22 | Payment Methods Screen | Saved cards, add new card, delete card, set default
M23 | Seller Dashboard Screen | Sales overview, charts, pending orders, quick actions
M24 | My Listings Screen | Product list, edit/delete, stock status, sales data
M25 | Add Product Screen | Product form, camera integration, image upload, save draft
M26 | Seller Orders Screen | Incoming orders, fulfill action, shipping labels
M27 | Messages/Inbox Screen | Message threads, unread badge, search, new message
M28 | Chat/Message Thread Screen | Conversation view, send message, attach photo, product context
M29 | Notifications Screen | All notifications, mark as read, filter by type
M30 | Trade Listings Screen | Available trades, filters, search
M31 | Create Trade Screen | Select items, trade terms, message, submit | MOBİLDEKİ HER ŞEYE TEKRAR BAKILMASI LAZIM AMA GENEL OLARAK HER ŞEY VAR
M32 | My Trades Screen | Active trades, offers sent/received, status
M33 | Settings Screen | Account settings, notifications, language, theme, logout
M34 | Notifications Settings Screen | Toggle notification types, sound, vibration
M35 | Language Settings Screen | Select language, apply changes
M36 | About Screen | App version, company info, contact, social links
M37 | Help/FAQ Screen | Categorized FAQs, search, contact support
M38 | Reviews Screen | Write review, rating, photo upload, submit
M39 | Filter Screen | All filters, price range slider, apply filters
M40 | Sort Options Screen | Sort by price, popularity, rating, newest

## 03 WEBSITE PAGES
Page Name | Category | Key Features/Components | User Type
Homepage | Core | Hero banner, featured products, categories, new arrivals, best sellers, search bar, promo banners | All Users
Product Listing Page | Core | Product grid/list view, filters (brand, scale, price, condition), sorting, pagination | All Users
Product Detail Page | Core | Images (zoom, 360° view), specs, price, add to cart, reviews, related products, seller info | All Users | 360 view
Search Results Page | Core | Search results, filters, sorting, suggestions, "did you mean", recent searches | All Users | elastic search güclenebilir
Shopping Cart | Core | Cart items, quantity adjustment, remove items, promo code, estimated total, save for later | Buyers
Checkout Page | Core | Shipping address, billing address, delivery options, payment method selection | Buyers
Payment Page | Core | Payment form, saved cards, new card entry, security badges, order summary | Buyers | saved cards
Order Confirmation Page | Core | Order details, order number, estimated delivery, download invoice, track order button | Buyers | download invoice , estimated delivery api gerekli
Collections Page | Browse | Curated collections (limited editions, vintage, racing, etc.), collection cards | All Users | koleksiyonlara kategori gerekiyor uçak koleksiyonları vb.
Manufacturers Page | Browse | List of all manufacturers (Hot Wheels, Matchbox, etc.), brand logos, product count | All Users
Manufacturer Detail Page | Browse | Brand info, all products by manufacturer, filters, brand story | All Users | manufacturer page , car model page , scales page ayrı olarak yok ilanlarımda filtrelenebilir
Car Models Page | Browse | Browse by real car model (Ford Mustang, Porsche 911, etc.), model images | All Users
Car Model Detail Page | Browse | All diecast versions of specific car model, variations, scales available | All Users
Scales Page | Browse | Browse by scale (1:18, 1:24, 1:43, 1:64, etc.), scale comparison guide | All Users
Scale Detail Page | Browse | All products in specific scale, size comparison, popular models | All Users
New Arrivals Page | Browse | Recently added products, sorted by date, filters | All Users
Best Sellers Page | Browse | Top selling products, trending items, popularity metrics | All Users | popularity mantığı soru işareti, top selling products mantığı yok şu an
Discounted Items Page | Browse | Sale products, discount percentage, original vs sale price, expiry timer | All Users
Accessories Page | Browse | Display cases, storage, tools, parts, filters by accessory type | All Users
Car Sets Page | Browse | Multi-pack sets, themed collections, bundle deals | All Users
Pre-Orders Page | Browse | Upcoming releases, pre-order products, release dates | All Users
Limited Editions Page | Browse | Rare and limited edition models, numbered editions, exclusives | All Users
Registration Page | Account | Sign up form, email verification, social login options, terms acceptance | Guest
Login Page | Account | Email/password login, social login, remember me, forgot password link | Guest
My Account Dashboard | Account | Overview of orders, wishlist, saved addresses, account stats, quick actions | Buyers
My Orders Page | Account | Order history, order status, tracking, reorder, download invoices | Buyers | re order ?
Order Detail Page | Account | Specific order details, items, tracking info, shipping address, invoice | Buyers
Order Tracking Page | Account | Real-time tracking, delivery status, carrier info, estimated delivery | Buyers | api gerekli
My Wishlist Page | Account | Saved products, add to cart, remove, share wishlist | Buyers
My Profile Page | Account | Personal info, profile picture, contact details, preferences | All Users
Address Book Page | Account | Saved addresses, add/edit/delete, set default shipping/billing | Buyers
Payment Methods Page | Account | Saved payment methods, add/remove cards, set default | Buyers
My Reviews Page | Account | User's product reviews, edit reviews, review history | Buyers
Account Settings Page | Account | Email preferences, notifications, privacy settings, language, currency | All Users | currency soru işareti
Change Password Page | Account | Current password, new password, confirm password | All Users
Forgot Password Page | Account | Email input, send reset link, confirmation message | Guest
Reset Password Page | Account | New password entry, confirm password, token validation | Guest
Email Verification Page | Account | Verify email token, success/error message, resend link | All Users
Sell on This Website Page | Seller | Seller benefits, how to sell, requirements, signup CTA, success stories | All Users | bu olacak mı ?
Seller Registration Page | Seller | Seller application form, business details, verification documents upload | Guest
Seller Dashboard | Seller | Sales overview, pending orders, inventory, analytics, quick actions | Sellers
My Listings Page | Seller | All seller's products, edit/delete listings, stock status, sales data | Sellers
Add Product Page | Seller | Product form (title, description, images, price, specs, inventory) | Sellers
Edit Product Page | Seller | Modify existing product details, update images, adjust pricing | Sellers
Seller Orders Page | Seller | Incoming orders, order status, fulfillment actions, shipping labels | Sellers
Seller Analytics Page | Seller | Sales reports, top products, revenue charts, customer insights | Sellers
Seller Profile Page | Seller | Public seller profile, ratings, reviews, product catalog, about seller | All Users
Trade/Swap Listings Page | Trade | Available items for trade, trade offers, filters, search | All Users
Create Trade Offer Page | Trade | Select items to trade, propose trade terms, add message | Buyers/Sellers
My Trade Offers Page | Trade | Sent/received trade offers, accept/reject/counter, negotiation thread | Buyers/Sellers
Trade Detail Page | Trade | Trade terms, items involved, messages, accept/decline actions | Buyers/Sellers
Messages/Inbox Page | Communication | Message threads, unread count, search messages, archive | All Users
Message Thread Page | Communication | Conversation view, send message, attach images, product context | All Users | attach image yok
Contact Seller Page | Communication | Message form to contact seller about specific product | Buyers
Notifications Page | Communication | All notifications, order updates, messages, trade offers, mark as read | All Users | read unread yok
Membership Plans Page | Membership | Membership tiers, benefits comparison, pricing, features list | All Users
Membership Signup Page | Membership | Select plan, payment info, membership benefits summary | Buyers
My Membership Page | Membership | Current plan, benefits, usage stats, upgrade/downgrade options | Members | downgrade yok
About Us Page | Information | Company story, mission, team, values, milestones | All Users
Contact Us Page | Information | Contact form, email, phone, address, social media links, map | All Users
FAQ Page | Information | Categorized FAQs, search, expandable Q&A, helpful links | All Users
Help Center Page | Information | Help topics, guides, tutorials, search, popular articles | All Users | tutorials olacak mı ?
Shipping & Delivery Page | Information | Shipping methods, costs, delivery times, international shipping, tracking | All Users | api gerekli
Returns & Exchanges Page | Information | Return policy, exchange process, refund timeline, conditions | All Users
Payment Options Page | Information | Accepted payment methods, payment security, installment options | All Users
Security Features Page | Information | Security measures, buyer protection, secure payments, data privacy | All Users
Size Guide Page | Information | Scale comparison chart, actual size measurements, scale explanations | All Users
Authenticity Guarantee Page | Information | Authentication process, counterfeit protection, verification badges | All Users
Collector's Guide Page | Information | Collecting tips, grading system, storage advice, valuation info | All Users
Privacy Policy Page | Legal | Data collection, usage, sharing, cookies, user rights, GDPR compliance | All Users
Terms of Service Page | Legal | User agreement, rules, liability, account terms, marketplace rules | All Users
Cookie Policy Page | Legal | Cookie types, usage, management, consent options | All Users
Refund Policy Page | Legal | Refund conditions, process, timeline, exceptions | All Users
Seller Agreement Page | Legal | Seller terms, commission, rules, prohibited items, account suspension | Sellers
Buyer Protection Page | Legal | Purchase protection, dispute resolution, money-back guarantee | Buyers
Intellectual Property Page | Legal | Copyright, trademark policy, DMCA, reporting infringement | All Users
Sitemap Page | Utility | HTML sitemap, all page links organized by category | All Users | tekrar bakılması gerekiyor
404 Error Page | Utility | Custom 404, search bar, popular categories, homepage link | All Users
500 Error Page | Utility | Server error message, refresh option, contact support | All Users
Maintenance Page | Utility | Maintenance message, estimated time, social media links | All Users
Coming Soon Page | Utility | Pre-launch page, email signup, countdown timer, social media | All Users
Newsletter Signup Page | Marketing | Email signup form, benefits, preferences, confirmation | All Users
Newsletter Unsubscribe Page | Marketing | Unsubscribe confirmation, preferences, feedback form | All Users
Advanced Search Page | Search | Detailed search filters, multiple criteria, save search | All Users | son aranılanlar yok
Compare Products Page | Search | Side-by-side comparison, specs table, price comparison, add to cart | All Users
Recently Viewed Page | Search | User's browsing history, quick re-access, clear history | All Users
Write Review Page | Reviews | Product review form, rating stars, photos upload, review guidelines | Buyers | chatgpt api bağlanacak
All Reviews Page | Reviews | All reviews for specific product, filter by rating, sort, helpful votes | All Users | chatgpt api bağlanacak

## 06 TESTING and QA
Task
Set up testing framework (Jest for unit tests)
Write unit tests for backend services (80%+ coverage)
Write unit tests for frontend components
Set up integration testing framework (Supertest)
Write integration tests for all API endpoints
Set up E2E testing framework (Cypress/Playwright)
Write E2E tests for critical user flows (15+ scenarios)
Perform cross-browser testing (Chrome, Firefox, Safari, Edge)
Perform mobile responsive testing (various screen sizes)
Test mobile apps on iOS devices (iPhone models)
Test mobile apps on Android devices (various manufacturers)
Set up load testing tools (JMeter/Artillery)
Perform load testing (500-1000 concurrent users)
Perform stress testing to find breaking points
Test payment gateway in sandbox environment
Test shipping integration functionality
Perform security testing (OWASP Top 10)
Conduct penetration testing
Perform accessibility testing (WCAG 2.1 AA)
Test email delivery and templates
Test push notifications on iOS and Android
Test multi-language functionality
Test GDPR compliance features (data export, deletion)
Regression testing after bug fixes
Create test documentation and reports

## 07 DEPLOYMENT
Task
Finalize production server configuration
Set up production SSL certificates
Configure production domain and DNS
Deploy database to production with initial data
Deploy backend API to production
Deploy web application to production
Configure CDN for production assets
Set up production monitoring dashboards
Configure production logging and alerts
Set up automated backup schedule
Configure email delivery service for production
Set up payment gateway in live mode
Configure shipping provider APIs for production
Enable Google Analytics and tracking in production
Submit mobile apps to App Store and Google Play
Perform smoke testing on production
Create production deployment checklist
Prepare rollback plan
Set up on-call rotation schedule
Create incident response procedures

## SECURITY CHECKLIST
Security Item | Details
SSL/TLS Certificate | Valid certificate, TLS 1.2+, A+ SSL Labs rating
HTTPS Enforcement | All traffic redirected to HTTPS, HSTS enabled
Security Headers | CSP, X-Frame-Options, X-Content-Type-Options configured
Input Validation | All user inputs validated on server-side
SQL Injection Prevention | Parameterized queries, ORM usage
XSS Prevention | Input sanitization, Content Security Policy
CSRF Protection | CSRF tokens on all state-changing requests
Password Security | bcrypt/Argon2 hashing, 12+ rounds, strong policy
Session Management | Secure cookies, httpOnly, SameSite, short expiration
Authentication | Rate limiting, account lockout, secure password reset
Authorization | Role-based access control, principle of least privilege
API Security | Rate limiting, API keys, OAuth 2.0 for third-party
Database Security | Encryption at rest, SSL connections, limited privileges
File Upload Security | Type validation, size limits, virus scanning | no virus detection
DDoS Protection | CDN-level protection, rate limiting
Payment Security | PCI DSS compliance, tokenization, no card storage
Error Handling | No sensitive info in errors, custom error pages
Logging & Monitoring | Security events logged, real-time alerts
Dependency Management | Regular updates, vulnerability scanning
Secrets Management | Environment variables, no hardcoded secrets
Backup Security | Encrypted backups, secure storage location
Incident Response | Documented procedures, contact list
Penetration Testing | Annual testing by third-party
Security Training | Developer security awareness training
Compliance | GDPR, PCI DSS documentation and implementation

## PERFORMANCE METRICS
Metric | Target | Measurement Method
Page Load Time (Desktop) | < 2 seconds | Google PageSpeed Insights, Lighthouse
Page Load Time (Mobile) | < 3 seconds | Google PageSpeed Insights, Lighthouse
Time to First Byte (TTFB) | < 200ms | Chrome DevTools, WebPageTest
First Contentful Paint (FCP) | < 1.8 seconds | Lighthouse, Web Vitals
Largest Contentful Paint (LCP) | < 2.5 seconds | Lighthouse, Web Vitals
First Input Delay (FID) | < 100ms | Lighthouse, Web Vitals
Cumulative Layout Shift (CLS) | < 0.1 | Lighthouse, Web Vitals
API Response Time (avg) | < 200ms | Application monitoring (New Relic/Datadog)
API Response Time (95th %ile) | < 500ms | Application monitoring
Database Query Time (avg) | < 50ms | Database monitoring, query logs
Server Response Time | < 100ms | Uptime monitoring, APM tools
Mobile App Launch Time | < 2 seconds | Firebase Performance, App analytics
Search Results Time | < 1 second | Application logs, user analytics
Image Load Time | < 1 second | Browser DevTools, synthetic monitoring
Uptime | 99.9% | Uptime monitoring (Pingdom/UptimeRobot)
Error Rate | < 0.1% | Error tracking (Sentry), application logs
Concurrent Users Capacity | 500-1000 | Load testing (JMeter/Artillery)
Cache Hit Rate | > 80% | Redis monitoring, CDN analytics
SSL Handshake Time | < 100ms | SSL testing tools
DNS Lookup Time | < 50ms | DNS monitoring tools

## COMPLIANCE
Requirement | Description
GDPR Compliance | EU data protection regulation - Privacy policy, consent management, data export/deletion
PCI DSS Compliance | Payment card industry security - Tokenization, no card storage, quarterly scans
Privacy Policy | Comprehensive, lawyer-reviewed privacy policy published
Terms of Service | Legal terms and conditions, lawyer-reviewed
Cookie Policy | Detailed cookie usage policy and consent banner
Refund Policy | Clear refund and return policy for customers
User Agreement | Marketplace user agreement for buyers and sellers
Data Protection Officer | Designated DPO (if required), contact information published
Right to Access | Users can request their personal data
Right to Erasure | Account deletion with data anonymization
Right to Rectification | Users can edit all personal information
Right to Data Portability | Export user data in machine-readable format (JSON/CSV)
Right to Object | Opt-out mechanisms for marketing and profiling
Consent Management | Track and manage user consent for data processing
Data Breach Notification | Procedures for notifying users within 72 hours
Age Verification | Mechanisms to prevent underage user registration
Copyright Protection | DMCA takedown procedures, user content policies
Trademark Protection | Verify sellers not selling counterfeit items
Anti-Money Laundering | Transaction monitoring, suspicious activity reporting
Tax Compliance | Sales tax collection and reporting mechanisms
Accessibility Compliance | WCAG 2.1 AA compliance for web and mobile
App Store Compliance | Apple App Store and Google Play Store guidelines
Seller Verification | KYC (Know Your Customer) for marketplace sellers
Content Moderation | Policies and tools for inappropriate content removal
Terms Updates | Mechanism to notify users of policy changes

## LAUNCH CHECKLIST
Item | Details
All features tested and working | Complete QA testing, no critical bugs
Load testing completed | System handles expected traffic load
Security audit completed | Penetration testing, vulnerability scan passed
SSL certificate installed | HTTPS working, SSL Labs A+ rating
DNS configured correctly | Domain pointing to production servers
CDN configured | Static assets served from CDN
Database backups tested | Backup restoration verified
Monitoring tools configured | APM, uptime, error tracking active
Analytics tracking verified | GA4, event tracking working correctly
Email delivery tested | All email templates working, SPF/DKIM/DMARC configured
Payment processing tested | Test transactions successful, webhooks working
Mobile apps submitted | iOS App Store and Google Play submissions approved
Push notifications working | FCM/APNs configured and tested
Legal pages published | Privacy Policy, Terms, Cookie Policy live
GDPR compliance verified | Cookie consent, data export/deletion working
SEO elements in place | Meta tags, sitemaps, robots.txt, structured data
Social media accounts created | Facebook, Instagram, Twitter profiles ready
Customer support setup | Help desk, live chat, FAQ ready
Admin panel tested | All admin functions working correctly
User documentation complete | Help guides, tutorials, FAQs published
Error pages customized | 404, 500 error pages designed and tested
Performance optimized | Core Web Vitals meeting targets
Multi-language tested | All languages display correctly, translations complete
Search functionality tested | All search features working, relevant results
Mobile responsive verified | Tested on various devices and screen sizes
Cross-browser tested | Chrome, Firefox, Safari, Edge compatibility verified
Accessibility tested | WCAG 2.1 compliance verified
Backup plan documented | Disaster recovery procedures in place
Rollback plan prepared | Ability to quickly revert if needed
Team trained | Support team trained on platform features
Marketing materials ready | Launch announcements, press releases prepared
Go-live date scheduled | Stakeholders informed, launch date confirmed

## DELIVERY CHECKLIST
Deliverable | Description
Website (97 pages) | Fully functional e-commerce website with all features
Mobile Apps (iOS & Android) | Native mobile apps with 41 screens and full functionality
Admin Panel (62 pages) | Complete admin dashboard for marketplace management
Database Schema | Complete database with all tables, relationships, and indexes
API Documentation | Comprehensive API documentation (Swagger/OpenAPI)
Technical Documentation | System architecture, deployment guide, maintenance procedures
User Manuals | End-user documentation and help guides
Admin Manual | Complete admin panel user guide
Source Code | Complete source code with version control repository access
Test Reports | Test plans, test cases, and test execution reports
Deployment Scripts | Automated deployment and infrastructure scripts
Training Materials | Video tutorials and training documentation
Security Audit Report | Penetration testing and security assessment report
Performance Report | Load testing results and optimization recommendations
GDPR Compliance Documentation | Privacy policy, cookie policy, data processing records
Payment Gateway Integration | PayTR and iyzico integration with Turkish Lira support
Shipping Integration | Integration with shipping provider APIs
SSL Certificates | Production SSL/TLS certificates configured
Monitoring Setup | APM, logging, error tracking, and uptime monitoring
Backup System | Automated backup system with tested restore procedures

## POST LAUNCH
Task | Frequency | Description
System Monitoring | Continuous | Monitor server health, application performance, error rates
Bug Fixes | As needed | Fix reported bugs and issues within 90-day warranty period
Security Updates | Weekly | Apply security patches to dependencies and frameworks
Database Backup Verification | Daily | Verify automated backups completed successfully
Performance Optimization | Monthly | Review and optimize slow queries, API endpoints
SSL Certificate Renewal | Annually | Renew SSL certificates before expiration
Dependency Updates | Monthly | Update libraries and dependencies (with testing)
Content Moderation | Daily | Review flagged content, approve listings and messages
User Support | Daily | Respond to user inquiries and support tickets
Log Analysis | Weekly | Review error logs and security logs
Database Optimization | Monthly | Optimize queries, rebuild indexes, clean old data
Storage Cleanup | Monthly | Remove orphaned files, optimize storage usage
Analytics Review | Weekly | Review traffic, conversions, user behavior
Load Testing | Quarterly | Perform load testing to ensure capacity
Security Scan | Monthly | Run automated security scans
Disaster Recovery Test | Quarterly | Test backup restore and failover procedures
Mobile App Updates | As needed | Submit bug fix updates to app stores
Email Deliverability Check | Weekly | Monitor email bounce rates and reputation
API Rate Limit Review | Monthly | Review and adjust rate limits based on usage
Feature Requests Review | Monthly | Evaluate and prioritize user feature requests