## Testing Checklist
🛒 tarodan.shop — End-User Testing Checklist (v2 — Full UI Coverage)
Mark Status for each test. Use Notes column to describe bugs. Priority: 🔴 Critical 🟠 High 🟡 Medium 🟢 Low
# | Category | Test Case | Expected Result | Actual Result | Status | Priority | Bug Notes / Steps to Reproduce
🏠 Homepage & First Impression
1 | Homepage & First Impression | Hero banner / slider loads and displays correctly | Banner visible, images render, text readable |  | ✅ Pass | 🟡 Medium
2 | Homepage & First Impression | Hero CTA buttons are clickable and go to correct pages | CTAs navigate to correct destination |  | ✅ Pass | 🟡 Medium
3 | Homepage & First Impression | Auto-playing slider/carousel advances correctly | Slides transition smoothly |  | ✅ Pass | 🟡 Medium
4 | Homepage & First Impression | Slider pause / prev / next controls work | User can manually control slides |  | ❌ Fail | 🟡 Medium | sliding part cant be manipulated manually
5 | Homepage & First Impression | Slider dots / pagination indicators update correctly | Active dot reflects current slide |  | ✅ Pass | 🟡 Medium
6 | Homepage & First Impression | Promotional banners / announcements are visible | Banners rendered correctly |  | ✅ Pass | 🟡 Medium
7 | Homepage & First Impression | Featured products section loads with products | Products displayed with image, name, price |  | ✅ Pass | 🟡 Medium
8 | Homepage & First Impression | New arrivals / best-sellers tabs on homepage work | Tab switch shows correct products |  | ✅ Pass | 🟡 Medium | Header says All listings instead of tab name
9 | Homepage & First Impression | Homepage loads fully without broken images | Zero broken image icons on page |  | ✅ Pass | 🟡 Medium
10 | Homepage & First Impression | Page does not show a flash of unstyled content (FOUC) | Styles applied on first render |  | ✅ Pass | 🟡 Medium
11 | Homepage & First Impression | Sticky header / announcement bar stays on scroll | Bar remains fixed while scrolling |  | ❌ Fail | 🟠 High | Bar doesn’t remain fixed while scrolling
🧭 Header, Navigation & Menus
12 | Header, Navigation & Menus | Logo is displayed and links back to homepage | Logo click → homepage |  | ✅ Pass | 🟡 Medium
13 |  |  | English language |  | ❌ Fail | 🟠 High | many places are still in Turkish after I click on Turkish
14 | Header, Navigation & Menus | Primary navigation bar links all work | Each nav item leads to correct page |  | ✅ Pass | 🟡 Medium
15 | Header, Navigation & Menus | Dropdown mega-menu opens on hover (desktop) | Dropdown appears on mouse hover |  | ❌ Fail | 🟠 High | Only categories open on hover- other tabs don’t
16 | Header, Navigation & Menus | Dropdown mega-menu opens on tap (mobile) | Dropdown opens on tap on mobile |  | ✅ Pass | 🟡 Medium
17 | Header, Navigation & Menus | Dropdown sub-category links navigate correctly | Sub-links go to correct category |  | ✅ Pass | 🟡 Medium
18 | Header, Navigation & Menus | Dropdown closes when clicking elsewhere | Menu dismisses on outside click |  | ✅ Pass | 🟡 Medium
19 | Header, Navigation & Menus | Active/current page is highlighted in nav | Current page nav item is styled differently |  | ❌ Fail | 🟡 Medium | Page is not highlighted
20 | Header, Navigation & Menus | Mobile menu shows all navigation items | All links accessible from mobile menu |  | ✅ Pass | 🟡 Medium
22 | Header, Navigation & Menus | Cart icon is visible in header | Cart icon present in header |  | ❌ Fail | 🟡 Medium | Because banner disappears
23 | Header, Navigation & Menus | Cart icon shows item count badge | Badge updates when items are added |  | ✅ Pass | 🟡 Medium
24 | Header, Navigation & Menus | Search icon/bar in header is accessible | Search opens on click/tap |  | ✅ Pass | 🟡 Medium
25 | Header, Navigation & Menus | language switcher works (if present) | Selection updates site /language |  | ✅ Pass | 🟡 Medium | Language selection should be in the header
26 | Header, Navigation & Menus | Header is fully visible on all screen sizes | No cropped or hidden header elements |  | ✅ Pass | 🟡 Medium
27 | Header, Navigation & Menus | Sticky header does not overlap content on scroll | Content not hidden behind header |  | ⚠️ Warning | 🟠 High | It does sometimes, pictures are in the front of the header
🗂️ Category & Collection Pages
28 | Category & Collection Pages | Category page loads all products | All products in category are shown |  | ⚠️ Warning | 🟡 Medium | Alignment is not good- All manufacturers link doesn’t do anything
28 | Category & Collection Pages | Category page title / heading is correct | Correct category name displayed |  | ❌ Fail | 🟡 Medium | It says all listing- and category isn't highlighted
29 | Category & Collection Pages | Category description text is displayed (if any) | Description renders correctly |  | ✅ Pass | 🟡 Medium
30 | Category & Collection Pages | Category banner image loads correctly | Banner visible without distortion |  | ❌ Fail | 🟡 Medium | Banner not visible
31 | Category & Collection Pages | Sub-category tabs switch content correctly | Clicking tab shows only that sub-category |  | ✅ Pass | 🟡 Medium
32 | Category & Collection Pages | Sub-category tabs highlight active tab | Active tab is visually distinct |  | ❌ Fail | 🟡 Medium | no Highlight
33 | Category & Collection Pages | 'View All' link in section loads full category | All products in category are shown |  | ✅ Pass | 🟡 Medium
34 | Category & Collection Pages | Product count is shown accurately | Product count matches visible products |  | ❌ Fail | 🟡 Medium | Doesn’t say the numbers of products found
35 | Category & Collection Pages | Empty category shows a friendly empty state | No Listing Yet' message shown |  | ✅ Pass | 🟡 Medium
36 | Category & Collection Pages | Category breadcrumb trail is correct | Breadcrumb: Home > Category |  | ✅ Pass | 🟡 Medium
37 | Category & Collection Pages | Pagination: Next page button loads more products | Next page shows next batch of products |  | ✅ Pass | 🟡 Medium
38 | Category & Collection Pages | Pagination: Previous page button works | Previous page returns to prior set |  | ✅ Pass | 🟡 Medium
39 | Category & Collection Pages | Pagination: Clicking a page number works | Correct page of products shown |  | ✅ Pass | 🟡 Medium
40 | Category & Collection Pages | Pagination: Current page number is highlighted | Active page number visually distinct |  | ✅ Pass | 🟡 Medium
41 | Category & Collection Pages | URL updates when navigating between pages/filters | URL reflects current page/filter state |  | ✅ Pass | 🟡 Medium
42 |  | Collection | Headers are visible from Collection tab |  | ❌ Fail | 🟡 Medium | Banner and header disappear completely
43 | Category & Collection Pages | Direct URL to paginated page loads correctly | Page 2 URL loads page 2 content |  | ✅ Pass | 🟡 Medium
🔽 Filters & Faceted Search
44 | Filters & Faceted Search | Filter by category/type works correctly | Products filtered to selected type |  | ❌ Fail | 🟡 Medium | Doesn’t work properly a lot of products doesn’t include the brand- to be added
45 | Filters & Faceted Search | Filter by price range works correctly | Only products in price range shown |  | ✅ Pass | 🟡 Medium
46 | Filters & Faceted Search | Price range min/max input fields work | Entering values filters correctly |  | ✅ Pass | 🟡 Medium
47 | Filters & Faceted Search | Filter by brand works correctly | Only selected brand products shown |  | ❌ Fail | 🟡 Medium | brand works only for cars and cycles
48 | Filters & Faceted Search | Filter by size works correctly | Only selected size products shown |  | ✅ Pass | 🟡 Medium
49 | Filters & Faceted Search | Filter by rating works correctly | Products filtered by star rating |  | ✅ Pass | 🟡 Medium
50 |  | Filter by brand works correctly | Products filtered by star Brand |  | ❌ Fail | 🟠 High | must show the available brands of the already filtered fields
51 | Filters & Faceted Search | Filter by availability (In Stock) works | Only in-stock products shown |  | ❌ Fail | 🟡 Medium | Out of stock / in stock not available
52 | Filters & Faceted Search | Multiple filters can be applied simultaneously | Combined filters produce correct results |  | ❌ Fail | 🟡 Medium | works only sometimes
53 | Filters & Faceted Search | Active filters are shown as tags/pills above results | Applied filters visible as removable tags |  | ✅ Pass | 🟡 Medium
54 | Filters & Faceted Search | Individual filter tag can be removed (X button) | Removing tag de-applies that filter |  | ✅ Pass | 🟡 Medium
55 | Filters & Faceted Search | 'Clear All Filters' / 'Reset' button removes all filters | All filters cleared, full list restored |  | ⚠️ Warning | 🟡 Medium | should also be added next to filter button- need multi filters
56 | Filters & Faceted Search | Filter count badge updates when filters applied | Badge shows number of active filters |  | ✅ Pass | 🟡 Medium
57 | Filters & Faceted Search | Filters persist on page reload / back navigation | Applied filters survive page navigation |  | ❌ Fail | 🟡 Medium | Doesn’t survive
58 | Filters & Faceted Search | Filters collapse/expand correctly (accordion on mobile) | Filter sections toggle on mobile |  | ✅ Pass | 🟡 Medium
59 | Filters & Faceted Search | Filter panel can be closed on mobile (overlay) | Filter drawer closes on X or outside tap |  | ✅ Pass | 🟡 Medium
60 | Filters & Faceted Search | Filter results show 'X results found' | Result count updates after filter |  | ❌ Fail | 🟡 Medium | Doesn’t give number
61 | Filters & Faceted Search | No-result filter state shows helpful message | 'No products match' shown with clear option |  | ⬜ Not Tested | 🟡 Medium
↕️ Sorting
62 | Sorting | Sort dropdown is visible on category/search pages | Sort control is present |  | ⚠️ Warning | 🟡 Medium | This sort shows the age of the model as Old or new, it should also give posting date
63 | Sorting | Sort by: Price Low to High works | Products ordered cheapest first |  | ✅ Pass | 🟡 Medium
64 | Sorting | Sort by: Price High to Low works | Products ordered most expensive first |  | ✅ Pass | 🟡 Medium
65 | Sorting | Sort by: Newest Arrivals works | Most recently added products appear first |  | ⚠️ Warning | 🟡 Medium | Should have posting Date
66 | Sorting | Sort by: Best Selling works | Best selling products ranked first |  | ⚠️ Warning | 🟡 Medium | What is the indicator? Number of clicks ?
67 | Sorting | Sort by: Top Rated / Avg. Rating works | Highest rated products appear first |  | ✅ Pass | 🟡 Medium
68 | Sorting | Sort by: A–Z (Name) works | Products sorted alphabetically A→Z |  | ✅ Pass | 🟡 Medium
69 | Sorting | Sort by: Z–A (Name) works | Products sorted alphabetically Z→A |  | ✅ Pass | 🟡 Medium
70 | Sorting | Sort by: Discount / % Off works (if applicable) | Highest discounted products first |  | ⚠️ Warning | 🟡 Medium | On On sale- it should include highest discount
71 | Sorting | Changing sort does not reset active filters | Filters remain applied after sort change |  | ✅ Pass | 🟡 Medium
72 | Sorting | Sort selection is shown as active in dropdown | Selected sort option is highlighted |  | ⚠️ Warning | 🟡 Medium | Should be better highlighted
73 | Sorting | Sort persists when navigating between pages | Sort order maintained on page 2+ |  | ❌ Fail | 🟡 Medium
74 | Sorting | URL updates when sort is changed | Sort param reflected in URL |  | ✅ Pass | 🟡 Medium
👁️ View Mode (Grid / List)
75 | View Mode (Grid / List) | Grid view button switches to grid layout | Products displayed in multi-column grid |  | ✅ Pass | 🟡 Medium
76 | View Mode (Grid / List) | List view button switches to list layout | Products displayed in single-column rows |  | ✅ Pass | 🟡 Medium
77 | View Mode (Grid / List) | Grid view shows correct columns (2, 3, 4 per row) | Column count matches selected option |  | ✅ Pass | 🟡 Medium
78 | View Mode (Grid / List) | List view shows extended product details | Description/attributes visible in list view |  | ✅ Pass | 🟡 Medium
79 | View Mode (Grid / List) | Active view mode button is visually highlighted | Active view icon appears selected |  | ✅ Pass | 🟡 Medium
80 | View Mode (Grid / List) | View preference persists across category navigation | Switching category keeps same view mode |  | ✅ Pass | 🟡 Medium
81 | View Mode (Grid / List) | All product images maintain aspect ratio in both views | No stretched or cropped images |  | ✅ Pass | 🟡 Medium
82 | View Mode (Grid / List) | Quick Add to Cart works from grid view | Product added without entering product page |  | ❌ Fail | 🟡 Medium | you have to open the product no matter the view- add quick add
83 | View Mode (Grid / List) | Quick View modal opens correctly from grid | Overlay shows product details |  | ✅ Pass | 🟡 Medium
84 | View Mode (Grid / List) | Quick View modal closes (X button / outside click) | Modal dismisses correctly |  | ❌ Fail | 🟡 Medium | Should be able to quick view and close without going back to the top of the listing
🔍 Search Functionality
85 | Search Functionality | Search bar is visible and accessible from all pages | Search always reachable |  | ❌ Fail | 🟡 Medium | It disappear sometimes
86 | Search Functionality | Search bar placeholder text is visible | Placeholder text shown |  | ✅ Pass | 🟡 Medium
87 | Search Functionality | Typing in search bar shows live / instant suggestions | Autocomplete dropdown appears |  | ❌ Fail | 🟡 Medium | Doesn’t auto completes
88 | Search Functionality | Clicking a suggestion navigates to that product/page | User lands on correct page |  | ✅ Pass | 🟡 Medium
89 | Search Functionality | Search suggestions include product images (if applicable) | Thumbnail shown in suggestion dropdown |  | ✅ Pass | 🟡 Medium
90 | Search Functionality | Recent searches are shown in dropdown (if applicable) | Previously searched terms appear |  | ✅ Pass | 🟡 Medium
91 | Search Functionality | Pressing Enter or clicking search icon submits query | Results page loads |  | ✅ Pass | 🟡 Medium
92 | Search Functionality | Search results page shows matching products | Products relevant to query are displayed |  | ❌ Fail | 🟡 Medium | many unrelated product appear while searching
93 | Search Functionality | Result count is shown on search results page | 'X products found' displayed |  | ❌ Fail | 🟡 Medium | Number of found product not shown
94 | Search Functionality | Searching with no results shows empty state message | 'No results for [query]' message shown |  | ✅ Pass | 🟡 Medium
95 | Search Functionality | Search works with partial words / keywords | Partial input returns relevant results |  | ❌ Fail | 🟡 Medium
96 | Search Functionality | Filters and sorting work on search results page | Filters apply to search results |  | ❌ Fail | 🟡 Medium
97 | Search Functionality | Clearing search input shows all products or returns home | Search cleared restores prior state |  | ✅ Pass | 🟡 Medium
98 | Search Functionality | Search modal/overlay closes with Escape key | Esc key closes search overlay |  | ✅ Pass | 🟡 Medium
99 | Search Functionality | Search modal/overlay closes with X button | X button closes search |  | ✅ Pass | 🟡 Medium
100 | Search Functionality | Mobile search experience is smooth | Keyboard doesn't obscure search results |  | ❌ Fail | 🟡 Medium | no search in mobile
🛍️ Product Detail Page (PDP)
101 | Product Detail Page (PDP) | Product title displays correctly | Product name matches listing |  | ✅ Pass | 🟡 Medium
102 | Product Detail Page (PDP) | Sale price and original price both shown (if on sale) | Strikethrough price + sale price visible |  | ⬜ Not Tested | 🟡 Medium
103 | Product Detail Page (PDP) | Discount percentage badge shown (if applicable) | e.g. '-20%' badge displayed |  | ✅ Pass | 🟡 Medium
104 | Product Detail Page (PDP) | Product images load correctly | All images render without error |  | ✅ Pass | 🟡 Medium
105 | Product Detail Page (PDP) | Main product image is large and high-quality | Main image clear, not pixelated |  | ✅ Pass | 🟡 Medium
106 | Product Detail Page (PDP) | Image gallery / thumbnails are clickable | Clicking thumbnail updates main image |  | ✅ Pass | 🟡 Medium
107 | Product Detail Page (PDP) | Image zoom works on hover (desktop) | Hover magnifies product image |  | ✅ Pass | 🟡 Medium
108 | Product Detail Page (PDP) | Image zoom works on pinch (mobile) | Pinch-to-zoom works on mobile |  | ✅ Pass | 🟡 Medium
110 | Product Detail Page (PDP) | Color/variant swatches are visible and selectable | Swatches rendered and clickable |  | ✅ Pass | 🟡 Medium
111 | Product Detail Page (PDP) | Quantity selector increments correctly | +/- buttons increase/decrease quantity |  | ⚠️ Warning | 🟡 Medium | pre populated product are sare showing 1 in stock
112 | Product Detail Page (PDP) | Quantity cannot exceed stock limit | Max qty enforced or stock message shown |  | ⚠️ Warning | 🟡 Medium | pre populated product are sare showing 1 in stock
113 | Product Detail Page (PDP) | 'Add to Cart' button works | Product added to cart |  | ✅ Pass | 🟡 Medium
114 | Product Detail Page (PDP) | 'Add to Cart' shows confirmation (toast / animation) | Visual feedback on add |  | ⬜ Not Tested | 🟡 Medium
115 |  | remove from cart |  |  | ❌ Fail |  | Doesn’t work
116 | Product Detail Page (PDP) | 'Buy Now' / direct checkout button works (if present) | Skips cart and goes to checkout |  | ✅ Pass | 🟡 Medium
117 | Product Detail Page (PDP) | Product description tab/section is readable | Full description displayed |  | ✅ Pass | 🟡 Medium
118 | Product Detail Page (PDP) | Tabs (Description, Details, Reviews, Shipping) switch correctly | Each tab shows its own content |  | ✅ Pass | 🟡 Medium
119 | Product Detail Page (PDP) | Active tab is highlighted | Active tab visually distinct |  | ❌ Fail | 🟡 Medium | doesn’t show which one is active
120 | Product Detail Page (PDP) | Product reviews / ratings section loads | Reviews displayed below fold |  | ✅ Pass | 🟡 Medium
121 | Product Detail Page (PDP) | Review star rating is visible and accurate | Star display matches numeric rating |  | ✅ Pass | 🟡 Medium
122 | Product Detail Page (PDP) | 'Write a Review' button / form works | Review form opens and submits |  | ⬜ Not Tested | 🟡 Medium
123 | Product Detail Page (PDP) | Related / You May Also Like products shown | Recommendation section loaded |  | ⬜ Not Tested | 🟡 Medium
124 | Product Detail Page (PDP) | Recently Viewed section shows prior products | Products user visited are shown |  | ⬜ Not Tested | 🟡 Medium
125 | Product Detail Page (PDP) | Share product buttons work (copy link / social) | Share functionality works |  | ❌ Fail | 🟡 Medium | Not available- may want to add
126 | Product Detail Page (PDP) | 'Back to Collection' link works | Returns to category page |  | ❌ Fail | 🟡 Medium | Doesn’t go back to exact place
127 | Product Detail Page (PDP) | Breadcrumb on PDP is correct | Home > Category > Product |  | ❌ Fail | 🟡 Medium | Doesn’t work all the time
128 | Product Detail Page (PDP) | Stock availability label is shown ('In Stock', 'Only X left') | Stock status visible to user |  | ⚠️ Warning | 🟡 Medium | All show 1
129 | Product Detail Page (PDP) | Out-of-stock product shows 'Notify Me' or disabled Add to Cart | OOS state handled gracefully |  | ⚠️ Warning | 🟡 Medium | Didn’t see anything out of stock- may add
130 | Product Detail Page (PDP) | 'Notify Me' email input and submit work | User can subscribe to restock alert |  | ❌ Fail | 🟡 Medium | No out of stock
131 | Product Detail Page (PDP) | Return policy summary shown on PDP | Return info accessible on product page |  | ⬜ Not Tested | 🟡 Medium
132 | Product Detail Page (PDP) | SKU / product code displayed | Product identifier visible |  | ❌ Fail | 🟡 Medium | No product code
🛒 Cart
134 | Cart | Cart page loads at /cart correctly | Cart page renders all items |  | ✅ Pass | 🟡 Medium
135 | Cart | Cart shows added product name, image, price, qty | All product info visible in cart |  | ✅ Pass | 🟡 Medium
136 | Cart | Cart shows variant details (size, color) | Selected variant shown in cart |  | ❌ Fail | 🟡 Medium | no details just seller
137 | Cart | Cart quantity can be increased | + button increments qty and updates total |  | ❌ Fail | 🟡 Medium | As there is just 1, cant test
138 | Cart | Cart quantity can be decreased | - button decrements qty and updates total |  | ❌ Fail | 🟡 Medium | As there is just 1, cant test
139 | Cart | Cart quantity can be edited via input field | Direct number input updates cart |  | ❌ Fail | 🟡 Medium | As there is just 1, cant test
140 | Cart | Remove / delete item from cart works | Item removed, total recalculates |  | ✅ Pass | 🟡 Medium
141 | Cart | Undo remove item option works (if present) | 'Undo' restores removed item |  | ❌ Fail | 🟡 Medium | Cant undo
142 | Cart | Cart total updates in real-time | Total changes immediately on qty change |  | ❌ Fail | 🟡 Medium | As there is just 1, cant test
143 | Cart | Cart shows subtotal correctly | Subtotal = sum of all item totals |  | ✅ Pass | 🟡 Medium
144 | Cart | Cart shows estimated shipping (if applicable) | Shipping cost or 'Calculated at checkout' |  | ❌ Fail | 🟡 Medium | didn’t calculate
145 | Cart | Cart shows estimated tax (if applicable) | Tax line visible |  | ❌ Fail | 🟡 Medium
146 | Cart | Cart shows savings / discount summary (if sale items) | Total savings shown |  | ❌ Fail | 🟡 Medium | No visible
147 | Cart | Valid promo code applies discount | Discount applied and shown |  | ❌ Fail | 🟡 Medium
148 | Cart | 'Continue Shopping' link works | Returns user to previous page / shop |  | ❌ Fail | 🟡 Medium | return doenst go all the way back
149 | Cart | 'Proceed to Checkout' button works | Navigates to checkout flow |  | ⬜ Not Tested | 🟡 Medium
150 | Cart | Cart persists after browser refresh | Items still in cart after F5 |  | ✅ Pass | 🟡 Medium
151 | Cart | Cart persists after closing and reopening browser tab | Items still in cart on next visit |  | ✅ Pass | 🟡 Medium
152 | Cart | Cart icon badge updates immediately on add/remove | Badge count reflects cart state |  | ✅ Pass | 🟡 Medium
153 | Cart | Empty cart shows friendly empty state message | 'Your cart is empty' with CTA |  | ✅ Pass | 🟡 Medium
154 | Cart | Gift note / order note field works (if present) | Message saved and visible in order |  | ⬜ Not Tested | 🟡 Medium
💳 Checkout Flow
155 | Checkout Flow | Checkout step 1: Contact / Email field accepts valid email | Valid email accepted |  | ✅ Pass | 🟡 Medium
156 | Checkout Flow | Checkout email validation rejects invalid formats | Error shown for bad email |  | ✅ Pass | 🟡 Medium
157 | Checkout Flow | Guest checkout proceeds without account required | Guest flow available |  | ✅ Pass | 🟡 Medium
158 | Checkout Flow | Checkout step 2: Shipping address form works | All fields accept correct input |  | ✅ Pass | 🟡 Medium
159 | Checkout Flow | Required field validation shows errors on empty submit | All required fields flagged |  | ⬜ Not Tested | 🟡 Medium
160 | Checkout Flow | Address autocomplete/suggestions appear (if applicable) | Suggestions appear while typing |  | ❌ Fail | 🟡 Medium
161 | Checkout Flow | State/Province field updates based on country selection | Correct states/provinces shown |  | ✅ Pass | 🟡 Medium
162 | Checkout Flow | Phone number field accepts correct format | Phone accepted with correct format |  | ⚠️ Warning | 🟡 Medium | Only accepts Turkish numbers
163 | Checkout Flow | Shipping method selection works | buttons selectable |  | ❌ Fail | 🟡 Medium | Just a field for credit card details
164 | Checkout Flow | Shipping cost updates when method is changed | Total updates on shipping change |  | ❌ Fail | 🟡 Medium | Didn’t calculate shipping cost
165 | Checkout Flow | Order summary is visible and accurate at checkout | Items, qty, price, totals correct |  | ⬜ Not Tested | 🟡 Medium
166 | Checkout Flow | Order summary can be collapsed/expanded (mobile) | Summary toggle works on mobile |  | ⬜ Not Tested | 🟡 Medium
167 | Checkout Flow | Promo code field works at checkout | Discount applies at checkout step |  | ⬜ Not Tested | 🟡 Medium
168 | Checkout Flow | Checkout step 3: Payment form loads correctly | Card fields rendered |  | ❌ Fail | 🟡 Medium
169 | Checkout Flow | Credit card number field accepts valid input | Card number formatted correctly |  | ✅ Pass | 🟡 Medium
170 | Checkout Flow | Expiry date field accepts MM/YY format | Date field works |  | ✅ Pass | 🟡 Medium
171 | Checkout Flow | CVV field accepts 3-4 digits | CVV field works |  | ✅ Pass | 🟡 Medium
172 | Checkout Flow | Card name field accepts text | Name on card input works |  | ✅ Pass | 🟡 Medium
173 | Checkout Flow | Invalid card number shows error | Error: 'Invalid card number' |  | ❌ Fail | 🟡 Medium | It just said that payment failed
174 |  | Card still shows chosen product | Product still in Cart |  | ❌ Fail |  | Product disappeared after unsuccessful payment- it later shows in cancelled section of my profile
175 | Checkout Flow | Expired card date shows error | Error: 'Card is expired' |  | ❌ Fail | 🟡 Medium | I kept in the cart for a week- still there
176 | Checkout Flow | PayPal / Apple Pay / Google Pay button works (if present) | Alternative payment method functional |  | ❌ Fail | 🟡 Medium | No such choices
177 | Checkout Flow | 'Place Order' button submits order | Order is placed successfully |  | ⬜ Not Tested | 🟡 Medium
178 | Checkout Flow | Loading state shown while order processes | Spinner or 'Processing...' shown |  | ⬜ Not Tested | 🟡 Medium
179 | Checkout Flow | Order confirmation page shown after successful purchase | Confirmation page with order # displayed |  | ⬜ Not Tested | 🟡 Medium
180 | Checkout Flow | Order number is visible on confirmation page | Order # shown prominently |  | ⬜ Not Tested | 🟡 Medium
181 | Checkout Flow | Order summary shown on confirmation page | Items and totals listed |  | ⬜ Not Tested | 🟡 Medium
182 | Checkout Flow | Estimated delivery date shown on confirmation | Delivery estimate visible |  | ⬜ Not Tested | 🟡 Medium
183 | Checkout Flow | Confirmation email received after purchase | Email arrives with order details |  | ⬜ Not Tested | 🟡 Medium
184 | Checkout Flow | Checkout progress steps indicator updates correctly | Step 1 → 2 → 3 highlights correctly |  | ✅ Pass | 🟡 Medium
185 | Checkout Flow | Can go back to previous checkout step without losing data | Back navigation keeps form data |  | ❌ Fail | 🟡 Medium | back works one step and then gets lost
186 | Checkout Flow | Terms & conditions checkbox required before placing order | Order blocked without T&C acceptance |  | ✅ Pass | 🟡 Medium
👤 User Account
187 | User Account | Registration page loads correctly | Registration form visible |  | ✅ Pass | 🟡 Medium
188 |  |  | link in the email for validation |  | ❌ Fail |  | No link visible
189 | User Account | Registration accepts valid inputs | Account created successfully |  | ✅ Pass | 🟡 Medium
190 | User Account | Registration rejects duplicate email | Error: 'Email already in use' |  | ⚠️ Warning | 🟡 Medium | Pass, but warning message was in Turkish while all the rest was in english
191 | User Account | Registration password strength indicator works (if present) | Indicator updates with password input |  | ✅ Pass | 🟡 Medium
192 | User Account | Registration requires password confirmation match | Error shown if passwords don't match |  | ✅ Pass | 🟡 Medium
193 | User Account | Login page loads correctly | Login form visible |  | ✅ Pass | 🟡 Medium
194 | User Account | Login with valid credentials works | User is logged in and redirected |  | ✅ Pass | 🟡 Medium
195 | User Account | Login with wrong password shows error | Error: 'Invalid credentials' |  | ⚠️ Warning | 🟡 Medium | Pass, but warning message was in Turkish while all the rest was in english
196 | User Account | Login with unregistered email shows error | Error: 'Email not found' |  | ⚠️ Warning | 🟡 Medium | Pass, but warning message was in Turkish while all the rest was in english
197 | User Account | 'Remember Me' checkbox keeps user logged in | Session persists after browser close |  | ❌ Fail | 🟡 Medium
198 | User Account | Forgot password page loads | Forgot password form accessible |  | ✅ Pass | 🟡 Medium
199 | User Account | Forgot password sends reset email | Reset email received |  | ❌ Fail | 🟡 Medium | email received but no link is visible
200 | User Account | Password reset link in email is functional | Link opens reset form |  | ❌ Fail | 🟡 Medium | No link visible
201 | User Account | New password can be set via reset form | Password updated successfully |  | ❌ Fail | 🟡 Medium
202 | User Account | Account dashboard loads after login | Dashboard with account info visible |  | ✅ Pass | 🟡 Medium
203 | User Account | My Orders section shows order history | Past orders listed correctly |  | ⚠️ Warning | 🟡 Medium | There is the space for
204 | User Account | Clicking an order shows order detail | Order detail page loads |  | ⬜ Not Tested | 🟡 Medium
205 | User Account | Order detail shows items, prices, status | All order info displayed |  | ⬜ Not Tested | 🟡 Medium
206 | User Account | Tracking link on order detail works (if applicable) | Tracking page opens |  | ❌ Fail | 🟡 Medium
207 | User Account | My Profile: name and email can be updated | Profile changes saved |  | ✅ Pass | 🟡 Medium | Need to do proper english translation
208 | User Account | My Profile: password can be changed | Password change works |  | ✅ Pass | 🟡 Medium | Need to do proper english translation
209 | User Account | My Addresses: new address can be added | Address saved to account |  | ✅ Pass | 🟡 Medium | Need to do proper english translation
210 | User Account | My Addresses: existing address can be edited | Address updates correctly |  | ✅ Pass | 🟡 Medium | Need to do proper english translation
211 | User Account | My Addresses: address can be deleted | Address removed from list |  | ✅ Pass | 🟡 Medium | Need to do proper english translation
212 | User Account | Default address can be set | Default address marked |  | ⬜ Not Tested | 🟡 Medium | Need to do proper english translation
213 | User Account | Notification preferences can be toggled (if present) | Notification settings saved |  | ⬜ Not Tested | 🟡 Medium | Need to do proper english translation
⭐ Reviews & Ratings
214 | Reviews & Ratings | Star rating display on product card is accurate | Stars match product rating |  | ❌ Fail | 🟡 Medium | Cant review
215 | Reviews & Ratings | Review count shown on product card | e.g. '(48 reviews)' |  | ❌ Fail | 🟡 Medium | reviewed products do not show how many revuews
216 | Reviews & Ratings | Reviews list loads on PDP | Individual reviews visible |  | ⚠️ Warning | 🟡 Medium | only for some products
217 | Reviews & Ratings | Reviews show author, date, rating, and body | All review fields displayed |  | ❌ Fail | 🟡 Medium
218 | Reviews & Ratings | Verified purchase badge shown on eligible reviews | Badge visible on verified reviews |  | ⬜ Not Tested | 🟡 Medium
219 | Reviews & Ratings | Reviews can be sorted (Most Recent, Most Helpful, etc.) | Sort order changes review list |  | ❌ Fail | 🟡 Medium
220 | Reviews & Ratings | Reviews can be filtered by star rating | Clicking star filter shows only those |  | ❌ Fail | 🟡 Medium
221 | Reviews & Ratings | Pagination / Load More on reviews works | More reviews load on demand |  | ❌ Fail | 🟡 Medium
222 | Reviews & Ratings | Write a Review form opens correctly | Review form modal or section loads |  | ❌ Fail | 🟡 Medium | Cant review unless I buy
223 | Reviews & Ratings | Review form: star selection works | Can select 1–5 stars |  | ❌ Fail | 🟡 Medium
224 | Reviews & Ratings | Review form: title and body fields work | Text input accepted |  | ❌ Fail | 🟡 Medium | Cant review unless I buy
225 | Reviews & Ratings | Review form: photo upload works (if allowed) | Photo attached to review |  | ❌ Fail | 🟡 Medium | Cant review unless I buy
226 | Reviews & Ratings | Review form: submit sends review for moderation | Confirmation: 'Review submitted' |  | ⬜ Not Tested | 🟡 Medium | Cant review unless I buy
📦 Order Tracking & Post-Purchase
227 | Order Tracking & Post-Purchase | Order tracking page is accessible | Tracking page loads |  | ⬜ Not Tested | 🟡 Medium
228 | Order Tracking & Post-Purchase | Tracking works with order number input | Status shown for valid order # |  | ⬜ Not Tested | 🟡 Medium
229 | Order Tracking & Post-Purchase | Invalid order number shows error | Error message displayed |  | ⬜ Not Tested | 🟡 Medium
230 | Order Tracking & Post-Purchase | Tracking timeline / status steps displayed | Processing → Shipped → Delivered shown |  | ⬜ Not Tested | 🟡 Medium
231 | Order Tracking & Post-Purchase | Carrier tracking link opens correct tracking page | External tracking URL works |  | ⬜ Not Tested | 🟡 Medium
232 | Order Tracking & Post-Purchase | Return / refund request form accessible | Return form loads |  | ⬜ Not Tested | 🟡 Medium
233 | Order Tracking & Post-Purchase | Return form submits correctly | Confirmation of return request shown |  | ⬜ Not Tested | 🟡 Medium
234 | Order Tracking & Post-Purchase | Download invoice / receipt works (if applicable) | PDF invoice downloads correctly |  | ⬜ Not Tested | 🟡 Medium
235 | Order Tracking & Post-Purchase | Re-order button adds items to cart (if applicable) | Previous order items added to cart |  | ⬜ Not Tested | 🟡 Medium
236 | Order Tracking & Post-Purchase | Cancel order option works (if within window) | Order cancellation initiates |  | ⬜ Not Tested | 🟡 Medium
🌐 Localization & Currency
237 | Localization & Currency | Correct currency displayed based on region | Currency matches user region |  | ⚠️ Warning | 🟡 Medium | only TRY
238 | Localization & Currency | Currency switcher changes all prices site-wide | All prices update on switch |  | ❌ Fail | 🟡 Medium | only TRY
239 | Localization & Currency | Language switcher changes all UI text (if applicable) | UI language changes globally |  | ❌ Fail | 🟡 Medium | change of language is not proper
240 | Localization & Currency | Date formats match locale (DD/MM/YY vs MM/DD/YY) | Dates shown in correct format |  | ❌ Fail | 🟡 Medium | NO dates
241 | Localization & Currency | Taxes shown correctly per region | VAT/Tax applied per locale |  | ❌ Fail | 🟡 Medium | No VAT calculation
🔔 Notifications & Emails
242 | Notifications & Emails | Welcome email received after registration | Welcome email arrives |  | ❌ Fail | 🟡 Medium | Welcome message was for the activation- Message body Turkish while I was using english
243 | Notifications & Emails | Password reset email arrives and link is not expired | Reset link valid and functional |  | ❌ Fail | 🟡 Medium | Reset message received- But NO Link visible- you have to click everywhere for it to work-Message body Turkish while I was using english
244 | Notifications & Emails | Newsletter signup confirmation email arrives | Confirmation email received |  | ❌ Fail | 🟡 Medium | No confirmation that the password was changed was received
245 | Notifications & Emails | All emails are mobile-friendly | Email renders correctly on mobile |  | ❌ Fail | 🟡 Medium | same issues
📄 Static & Informational Pages
246 | Static & Informational Pages | About Us page loads and displays content | Page renders with text and images |  | ✅ Pass | 🟡 Medium
247 | Static & Informational Pages | Contact Us page loads correctly | Contact info and/or form visible |  | ❌ Fail | 🟡 Medium
248 | Static & Informational Pages | Contact form submits and shows confirmation | 'Message sent' confirmation shown |  | ⚠️ Warning | 🟡 Medium | update contact details - I sent a message - let me know if it was received
249 | Static & Informational Pages | FAQ / Help page loads and content is correct | All FAQ items visible |  | ⚠️ Warning | 🟡 Medium | In Turkish
250 | Static & Informational Pages | Shipping & Returns policy page loads | Policy page loads with content |  | ⚠️ Warning | 🟡 Medium | In Turkish
251 | Static & Informational Pages | Terms & Conditions page loads | T&C page loads with content |  | ⚠️ Warning | 🟡 Medium | In Turkish

## Summary Dashboard
📊 tarodan.shop — Test Run Summary
📋 Test Run Information
Tester Name
Test Date
Environment | Staging / Production
URL Tested | https://tarodan.shop
Browser(s)
Device(s)
OS
Overall Result
📈 Test Results Summary
Metric | Count | % of Total | Status
Total Test Cases | 265 | —
✅ Passed | 110 | 41.51% | 🎯 Target: 100%
❌ Failed | 80 | 30.19% | 🚨 Target: 0%
⚠️ Warnings | 23 | 8.679%
🔄 In Progress | 0 | 0%
⏭️ Skipped | 0 | 0%
⬜ Not Tested | 36 | 13.58% | ⏳ Complete before sign-off